## Sheet1
Issue No. | Issue Name | Component | Description | Status | Done By | Type
FDB-1 | First pick of draft not removed | Draft Board | The first pick of the draft isn't removed from the free agent list after being drafted, but does show up on the roster for the team that drafted the player. | Verify
FDB-2 | Roster control not updating | Draft Board | The UI upon removing players from a roster only updates for first team in nomination order. For all other members, the admin must click off the member and click back on the member to see the player removed from the roster | Verify
FDB-3 | Scroller postion on roster control | Draft Board | Move the vertical scroller on the roster control to within the accordion so that as the accordion expands to accomidate players the admin scrolls just the roster control | Verify
FDB-4 | Scroller position on free agent control | Draft Board | Move the vertical scroller on the free agent control to within the list of players so that the sort, search, and tabs remain visible as the user scrolls through the list of free agents | verify
FDB-5 | Scroller position on tab control in center of draft board | Draft Board | Move the vertical scroll of the tab control that displays depth chart and rosters so that only the content scrolls and the tabs remain visible | Verify
FDB-6 | ber logos don't scale | Draft Board | If you change the resolution of the draft board the member logos do not scale properly and appear distored. The other images do not have this issue. |  | Designer
FDB-7 | Add Edit Link to the "Your Drafts" control on Dashboard page for any draft the user is the admin more | Dashboard | An admin should have the ability to edit their draft settings for any draft they are the admin of. The edit link can be located on the "Your Drafts" control on the Dashboard page |  |  | New Feature
FDB-8 | Print Draft Results | Draft Board | Within the content section of the Roster tab control in center of draft board should be a button that prints the content of that control. The button should say "Print Rosters" and launch another windows that displays rosters for all fantasy teams. | Verify
FDB-9 | Player Details Tab | Draft Board | Add another tab to the NFL Depth Chart/Roster control in center of draft board called "Player". This will display content as depecticted in the wireframe |  |  | New Feature
FDB-10 | UI Draft Event Occurred Indicator | Draft Board | Non-Admin members of the draft that are viewing the draft board and may not be looking at the fantasy roster, or free agent list that was updated by the draft admin have no idea that an event took place. We need a UI indication that informs them in real time when a draft event takes place |  | Designer
FDB-11 | Last 5 drafted players | Draft Board | "Add a tab in the center main content section of the draft board called ""Last 5 Picks"". This will display the following columns with the associated data fields for the last 5 players that were drafted. The content should update in real time as players are drafted. 1. Pick # (The order the player was drafted.) 2. Name (Player Name) 3. Position 4. Amount (Auction Draft Only) 5. Team (Fantasy Team that drafted the player)" |  |  | New Feature
FDB-12 | Alert on lost internet connection | Draft Board | If the user attempts to make an updated to the draft board and there isn't an internet connection, display a message to the user that says "Draftboard has lost connection to the network." | Verify
FDB-13 | Member logo placeholder on setup | Draft Setup | After adding a member from the member setup tab, the placeholder containing logo of the member added needs to clear out similar to the other input fields. "1. Create a new draft 2. Add a member from the member's tab of the setup and include a logo. 3. Click ""Add Member"" 4. Notice that the logo remains in the place holder. It should clear out." Activity |  | Designer (Need to find the way so it should work with safarai)
FDB-14 | Fixed team header on depth chart and fantasy rosters | Draft Board | When scrolling though the content depth charts and fantasy rosters tabs the team names should operate as a fixed header until the list of players from the next team are viewable. |  | Designer
FDB-15 | Size of member salary cap | Draft Board | The salary cap value needs to be bigger. During live in-person drafts(where members are physically present and all are viewing the projected draft board) it's hard for members to see the salary cap amount for each member. This needs to be bigger | Verify
FDB-16 | Trade button | Draft Board | Add a button with title "Trade" on the member roster control next to the "Update" button that opens an overlay window with the Trade view. The content of this view can be empty for now until I develop wireframe | Verify |  | New Feature
FDB-17 | Team Name Roster #0 | Draft Board | The Roster control only updates for fantasy teams that have players on their roster. If I select a fantasy team from top of draft board that has not drafted any players I would expect the Roster control header to change to "Team Name (that was selected) Roster #0. | Verify
FDB-18 | Fantasy Rosters Tab | Draft Board | The last build appears to have broken the fantasy rosters tab on Draft Information Section | Verify
1. Browse to any draft board that has players on member roster and click the Fantasy Rosters tab
FDB-19 | Fantasy Draft Board | Draft Board | Real Time Update Errors For Other Browser Instances 1. Open 2 browser instances of the same auction draft 2. Draft a player with an price of $45 from one of the browser instances 3. Now view the second browser instance and you will see that the SalaryCap amount remaining for that member has a different $ amount than the $ amount shown in the first browser instance. You will also notice that the player drafted from the first browser instance is still displaying in the free agent list of the second browser instance when it should have been removed since the player was drafted
FDB-20 | Auto login |  | 1. Open browser and login to firedraft.azurewebsites.net 2. Close browser 3. Open browser and browser to firedraft.azturewebsites.net -The expected behavior would be that the user would have to login to the site again -Currently the user is redirected to the dashboard page automatically. This represents a security issue as it could allow a user to access someone else's draft account if they happened to browse to the site after someone else logged in and assumed that closing the browser would kill the session.
FDB-21 |  |  | Draft Admin role for user that is creating the private draft The members tab of the draft setup currently has the options for 1. View Only: This allows a member to access the private draft board without any drafting permissions. 2. Remote Drafter: This allows a member to access the private draft board and only draft players onto their fantasy team. 3. Draft Admin: This is allows a member to access the private draft board and draft players for any member of the draft board. Upon arriving at the members tab of the setup, the user's default role should be Draft Admin since that user is creating the draft. All other members added by the user should have a default role of "View Only"